## Acitvity
Activity | Predecessor | Optimistic | Most Likely | Pessimistic | Expected Time | Variance
Start
Document Process
1. Define Project Scope |  | 3 | 5 | 7 | 5 | 0.44444
2. Conduct Stackholder Analysis | 1 | 4 | 6 | 7 | 5.8333 | 0.25
3. Create Project Charter | 1,2 | 3 | 4 | 6 | 4.1667 | 0.25
4. Identify Document Requirments | 3 | 3 | 4 | 5 | 4 | 0.11111
5. Obtain necessary permissons | 4 | 5 | 7 | 9 | 7 | 0.44444
6. Confirmation of Local Fire Department Partnership | 5 | 6 | 8 | 11 | 8.1667 | 0.69444
7. Develop Safety Training Protocol | 6 | 5 | 8 | 10 | 7.8333 | 0.69444
8. Review Documentation | 5,6,7 | 3 | 4 | 6 | 4.1667 | 0.25
Training Preparation
9. Identify Learning Objectives | 8 | 3 | 6 | 9 | 6 | 1
10. Desing Training Materials Template | 9 | 3 | 4 | 6 | 4.1667 | 0.25
11. Develop Training Modules | 10 | 5 | 7 | 9 | 7 | 0.44444
12. Design Lesson Plans | 9,11 | 3 | 5 | 7 | 5 | 0.44444
13. Create Interactive Activities | 12 | 4 | 6 | 8 | 6 | 0.44444
14. Prepare Visual Aids | 11,13 | 4 | 6 | 8 | 6 | 0.44444
15. Gather Necessary Materials | 14 | 4 | 5 | 7 | 5.1667 | 0.25
16. Secure Fire Extinguisher | 15 | 3 | 4 | 6 | 4.1667 | 0.25
17. Co-ordinate with Fire Safety Experts | 16 | 3 | 5 | 8 | 5.1667 | 0.69444
18. Schedule Training Sessions | 15,17 | 3 | 4 | 6 | 4.1667 | 0.25
19. Arrange Transportation | 15,16,18 | 3 | 4 | 6 | 4.1667 | 0.25
20. Assemble Training Kits | 18,19 | 3 | 5 | 7 | 5 | 0.44444
21. Prepare Training Sign-Up Sheets | 17 | 3 | 5 | 8 | 5.1667 | 0.69444
22. Develop Pre-Assessment Tests | 21 | 2 | 4 | 6 | 4 | 0.44444
23. Train Instructors | 21,22 | 4 | 6 | 9 | 6.1667 | 0.69444
24. Notify School Administrator | 20,23 | 3 | 5 | 7 | 5 | 0.44444
25. Finalize Training Agenda | 24 | 3 | 6 | 8 | 5.8333 | 0.69444
Training Delivery
26. Conduct Pre-Assessment Tests | 25 | 1 | 2 | 3 | 2 | 0.11111
27. Set Up Training Ground | 26 | 1 | 2 | 3 | 2 | 0.11111
28. Deliver Training Modules | 25,27 | 2 | 3 | 5 | 3.1667 | 0.25
29. Demostrate Fire Extinguisher Usage | 27 | 1 | 2 | 3 | 2 | 0.11111
30. Facilitate Interactive Activities | 27,28,29 | 1 | 2 | 3 | 2 | 0.11111
31. Provide Hands-On Training | 30 | 1 | 2 | 3 | 2 | 0.11111
32. Administer Post Assessment Tests | 30,31 | 1 | 3 | 4 | 2.8333 | 0.25
33. Collect Training Evaluation Forms | 32 | 2 | 3 | 4 | 3 | 0.11111
34. Gather Feedback from Instructors | 33 | 1 | 2 | 3 | 2 | 0.11111
35. Gather Feedback From Students | 33,34 | 1 | 2 | 3 | 2 | 0.11111
Project Closure
36. Evaluate Effectiveness of Training | 34,35 | 2 | 3 | 4 | 3 | 0.11111
37. Review Feedback | 36 | 2 | 3 | 4 | 3 | 0.11111
38. Analyze Evaluation Data | 37 | 3 | 4 | 6 | 4.1667 | 0.25
39. Conduct Post-Project Review Meeting | 38 | 2 | 5 | 6 | 4.6667 | 0.44444
40. Share Results with Stackholders | 39 | 4 | 6 | 8 | 6 | 0.44444
41. Archive Project Documentation | 40 | 3 | 5 | 8 | 5.1667 | 0.69444
42. Farewell Party for Contributors | 41 | 3 | 5 | 7 | 5 | 0.44444
43. Close Project Accounts | 42 | 3 | 5 | 9 | 5.3333 | 1
Finish

## NT,CT
Activity | Predecessor | Normal Time | Crash Time
Start
Document Process
1. Define Project Scope |  | 5 | 3
2. Conduct Stackholder Analysis | 1 | 5.8333 | 4
3. Create Project Charter | 1,2 | 4.1667 | 3
4. Identify Document Requirments | 3 | 4 | 3
5. Obtain necessary permissons | 4 | 7 | 5
6. Confirmation of Local Fire Department Partnership | 5 | 8.1667 | 6
7. Develop Safety Training Protocol | 6 | 7.8333 | 5
8. Review Documentation | 5,6,7 | 4.1667 | 3
Training Preparation
9. Identify Learning Objectives | 8 | 6 | 3
10. Desing Training Materials Template | 9 | 4.1667 | 3
11. Develop Training Modules | 10 | 7 | 5
12. Design Lesson Plans | 9,11 | 5 | 3
13. Create Interactive Activities | 12 | 6 | 4
14. Prepare Visual Aids | 11,13 | 6 | 4
15. Gather Necessary Materials | 14 | 5.1667 | 4
16. Secure Fire Extinguisher | 15 | 4.1667 | 3
17. Co-ordinate with Fire Safety Experts | 16 | 5.1667 | 3
18. Schedule Training Sessions | 15,17 | 4.1667 | 3
19. Arrange Transportation | 15,16,18 | 4.1667 | 3
20. Assemble Training Kits | 18,19 | 5 | 3
21. Prepare Training Sign-Up Sheets | 17 | 5.1667 | 3
22. Develop Pre-Assessment Tests | 21 | 4 | 2
23. Train Instructors | 21,22 | 6.1667 | 4
24. Notify School Administrator | 20,23 | 5 | 3
25. Finalize Training Agenda | 24 | 5.8333 | 3
Training Delivery
26. Conduct Pre-Assessment Tests | 25 | 2 | 1
27. Set Up Training Ground | 26 | 2 | 1
28. Deliver Training Modules | 25,27 | 3.1667 | 2
29. Demostrate Fire Extinguisher Usage | 27 | 2 | 1
30. Facilitate Interactive Activities | 27,28,29 | 2 | 1
31. Provide Hands-On Training | 30 | 2 | 1
32. Administer Post Assessment Tests | 30,31 | 2.8333 | 1
33. Collect Training Evaluation Forms | 32 | 3 | 2
34. Gather Feedback from Instructors | 33 | 2 | 1
35. Gather Feedback From Students | 33,34 | 2 | 1
Project Closure
36. Evaluate Effectiveness of Training | 34,35 | 3 | 2
37. Review Feedback | 36 | 3 | 2
38. Analyze Evaluation Data | 37 | 4.1667 | 3
39. Conduct Post-Project Review Meeting | 38 | 4.6667 | 2
40. Share Results with Stackholders | 39 | 6 | 4
41. Archive Project Documentation | 40 | 5.1667 | 3
42. Farewell Party for Contributors | 41 | 5 | 3
43. Close Project Accounts | 42 | 5.3333 | 3
Finish

## ES EF LS LF
Activity | Activity time | Early Start | Early Finish | Late Start | Late Finish | Slack
Project | 194
1 | 5 | 0 | 5 | 0 | 5 | 0
2 | 5.8 | 5 | 10.8 | 5 | 10.8 | 0
3 | 4.2 | 10.8 | 15 | 10.8 | 15 | 0
4 | 4 | 15 | 19 | 15 | 19 | 0
5 | 7 | 19 | 26 | 19 | 26 | 0
6 | 8.2 | 26 | 34.2 | 26 | 34.2 | 0
7 | 7.8 | 34.2 | 42 | 34.2 | 42 | 0
8 | 4.2 | 42 | 46.2 | 42 | 46.2 | 0
9 | 6 | 46.2 | 52.2 | 46.2 | 52.2 | 0
10 | 4.2 | 52.2 | 56.4 | 52.2 | 56.4 | 0
11 | 7 | 56.4 | 63.4 | 56.4 | 63.4 | 0
12 | 5 | 63.4 | 68.4 | 63.4 | 68.4 | 0
13 | 6 | 68.4 | 74.4 | 68.4 | 74.4 | 0
14 | 6 | 74.4 | 80.4 | 74.4 | 80.4 | 0
15 | 5.2 | 80.4 | 85.6 | 80.4 | 85.6 | 0
16 | 4.2 | 85.6 | 89.8 | 85.6 | 89.8 | 0
17 | 5.2 | 89.8 | 95 | 89.8 | 95 | 0
18 | 4.2 | 95 | 99.2 | 97 | 101.2 | 2
19 | 4.2 | 99.2 | 103.4 | 101.2 | 105.4 | 2
20 | 5 | 103.4 | 108.4 | 105.4 | 110.4 | 2
21 | 5.2 | 95 | 100.2 | 95 | 100.2 | 0
22 | 4 | 100.2 | 104.2 | 100.2 | 104.2 | 0
23 | 6.2 | 104.2 | 110.4 | 104.2 | 110.4 | 0
24 | 5 | 110.4 | 115.4 | 110.4 | 115.4 | 0
25 | 5.8 | 115.4 | 121.2 | 115.4 | 121.2 | 0
26 | 2 | 121.2 | 123.2 | 121.2 | 123.2 | 0
27 | 2 | 123.2 | 125.2 | 123.2 | 125.2 | 0
28 | 3.2 | 125.2 | 128.4 | 125.2 | 128.4 | 0
29 | 2 | 125.2 | 127.2 | 126.4 | 128.4 | 1.2
30 | 2 | 128.4 | 130.4 | 128.4 | 130.4 | 0
31 | 2 | 130.4 | 132.4 | 130.4 | 132.4 | 0
32 | 2.8 | 132.4 | 135.2 | 132.4 | 135.2 | 0
33 | 3 | 135.2 | 138.2 | 135.2 | 138.2 | 0
34 | 2 | 138.2 | 140.2 | 138.2 | 140.2 | 0
35 | 2 | 140.2 | 142.2 | 140.2 | 142.2 | 0
36 | 3 | 142.2 | 145.2 | 142.2 | 145.2 | 0
37 | 3 | 145.2 | 148.2 | 145.2 | 148.2 | 0
38 | 4.2 | 148.2 | 152.4 | 148.2 | 152.4 | 0
39 | 4.7 | 152.4 | 157.1 | 152.4 | 157.1 | 0
40 | 6 | 157.1 | 163.1 | 157.1 | 163.1 | 0
41 | 5.2 | 163.1 | 168.3 | 163.1 | 168.3 | 0
42 | 5 | 168.3 | 173.3 | 168.3 | 173.3 | 0
43 | 5.3 | 173.3 | 178.6 | 173.3 | 178.6 | 0

## NC CC
Activity | Predecessor | Normal Time | Crash Time | Normal Cost | Crash Cost | Maximum Time Reduction | Cost of Crashing Per Week
Start
Document Process
1. Define Project Scope |  | 5 | 3 | 1100000 | 1200000 | 2 | 50000
2. Conduct Stackholder Analysis | 1 | 5.8333 | 4 | 1011200 | 1051200 | 1.8333 | 21818.1818
3. Create Project Charter | 1,2 | 4.1667 | 3 | 588000 | 610000 | 1.1667 | 18857.1429
4. Identify Document Requirments | 3 | 4 | 3 | 560000 | 580000 | 1 | 20000
5. Obtain necessary permissons | 4 | 7 | 5 | 980000 | 1000000 | 2 | 10000
6. Confirmation of Local Fire Department Partnership | 5 | 8.1667 | 6 | 1404800 | 1504800 | 2.1667 | 46153.8462
7. Develop Safety Training Protocol | 6 | 7.8333 | 5 | 1827600 | 1845600 | 2.8333 | 6352.9412
8. Review Documentation | 5,6,7 | 4.1667 | 3 | 924000 | 950000 | 1.1667 | 22285.7143
Training Preparation
9. Identify Learning Objectives | 8 | 6 | 3 | 1368000 | 1395000 | 3 | 9000
10. Desing Training Materials Template | 9 | 4.1667 | 3 | 1041600 | 1060600 | 1.1667 | 16285.7143
11. Develop Training Modules | 10 | 7 | 5 | 1344000 | 1374000 | 2 | 15000
12. Design Lesson Plans | 9,11 | 5 | 3 | 960000 | 990000 | 2 | 15000
13. Create Interactive Activities | 12 | 6 | 4 | 1152000 | 1182000 | 2 | 15000
14. Prepare Visual Aids | 11,13 | 6 | 4 | 864000 | 894000 | 2 | 15000
15. Gather Necessary Materials | 14 | 5.1667 | 4 | 798800 | 800500 | 1.1667 | 1457.1429
16. Secure Fire Extinguisher | 15 | 4.1667 | 3 | 626200 | 666200 | 1.1667 | 34285.7143
17. Co-ordinate with Fire Safety Experts | 16 | 5.1667 | 3 | 1185600 | 1205600 | 2.1667 | 9230.7692
18. Schedule Training Sessions | 15,17 | 4.1667 | 3 | 355200 | 395200 | 1.1667 | 34285.7143
19. Arrange Transportation | 15,16,18 | 4.1667 | 3 | 235200 | 285200 | 1.1667 | 42857.1429
20. Assemble Training Kits | 18,19 | 5 | 3 | 1000000 | 1100000 | 2 | 50000
21. Prepare Training Sign-Up Sheets | 17 | 5.1667 | 3 | 291200 | 301200 | 2.1667 | 4615.3846
22. Develop Pre-Assessment Tests | 21 | 4 | 2 | 800000 | 850000 | 2 | 25000
23. Train Instructors | 21,22 | 6.1667 | 4 | 1413600 | 1463600 | 2.1667 | 23076.9231
24. Notify School Administrator | 20,23 | 5 | 3 | 700000 | 750000 | 2 | 25000
25. Finalize Training Agenda | 24 | 5.8333 | 3 | 1647200 | 1667200 | 2.8333 | 7058.8235
Training Delivery
26. Conduct Pre-Assessment Tests | 25 | 2 | 1 | 350000 | 380000 | 1 | 30000
27. Set Up Training Ground | 26 | 2 | 1 | 175000 | 195000 | 1 | 20000
28. Deliver Training Modules | 25,27 | 3.1667 | 2 | 962600 | 1002600 | 1.1667 | 34285.7143
29. Demostrate Fire Extinguisher Usage | 27 | 2 | 1 | 426000 | 526000 | 1 | 100000
30. Facilitate Interactive Activities | 27,28,29 | 2 | 1 | 522000 | 592000 | 1 | 70000
31. Provide Hands-On Training | 30 | 2 | 1 | 426000 | 496000 | 1 | 70000
32. Administer Post Assessment Tests | 30,31 | 2.8333 | 1 | 462000 | 482000 | 1.8333 | 10909.0909
33. Collect Training Evaluation Forms | 32 | 3 | 2 | 756000 | 796000 | 1 | 40000
34. Gather Feedback from Instructors | 33 | 2 | 1 | 456000 | 484000 | 1 | 28000
35. Gather Feedback From Students | 33,34 | 2 | 1 | 182000 | 192000 | 1 | 10000
Project Closure
36. Evaluate Effectiveness of Training | 34,35 | 3 | 2 | 898000 | 918000 | 1 | 20000
37. Review Feedback | 36 | 3 | 2 | 564000 | 594000 | 1 | 30000
38. Analyze Evaluation Data | 37 | 4.1667 | 3 | 588000 | 608000 | 1.1667 | 17142.8571
39. Conduct Post-Project Review Meeting | 38 | 4.6667 | 2 | 1560400 | 1590400 | 2.6667 | 11250
40. Share Results with Stackholders | 39 | 6 | 4 | 900000 | 930000 | 2 | 15000
41. Archive Project Documentation | 40 | 5.1667 | 3 | 291200 | 301200 | 2.1667 | 4615.3846
42. Farewell Party for Contributors | 41 | 5 | 3 | 940000 | 970000 | 2 | 15000
43. Close Project Accounts | 42 | 5.3333 | 3 | 1123600 | 1143600 | 2.3333 | 8571.4286
Finish |  | 193.6667 | 122

## Crashing
Activity | Normal time | Crash time | Normal Cost | Crash Cost | Crash cost/pd | Crash by | Crashing cost
Project | 194 | 122
1 | 5 | 3 | 1100000 | 1200000 | 50000 | 2 | 100000
2 | 5.8 | 4 | 1011200 | 1051200 | 22222.22 | 1.8 | 39999.996
3 | 4.2 | 3 | 588000 | 610000 | 18333.34 | 1.2 | 22000.008
4 | 4 | 3 | 560000 | 580000 | 20000 | 1 | 20000
5 | 7 | 5 | 980000 | 1000000 | 10000 | 2 | 20000
6 | 8.2 | 6 | 1404800 | 1504800 | 45454.55 | 2.2 | 100000.01
7 | 7.8 | 5 | 1827600 | 1845600 | 6428.57 | 2.8 | 17999.996
8 | 4.2 | 3 | 924000 | 950000 | 21666.67 | 1.2 | 26000.004
9 | 6 | 3 | 1368000 | 1395000 | 9000 | 3 | 27000
10 | 4.2 | 3 | 1041600 | 1060600 | 15833.34 | 1.2 | 19000.008
11 | 7 | 5 | 1344000 | 1374000 | 15000 | 2 | 30000
12 | 5 | 3 | 960000 | 990000 | 15000 | 2 | 30000
13 | 6 | 4 | 1152000 | 1182000 | 15000 | 2 | 30000
14 | 6 | 4 | 864000 | 894000 | 15000 | 2 | 30000
15 | 5.2 | 4 | 798800 | 800500 | 1416.67 | 3 | 4250.01
16 | 4.2 | 3 | 626200 | 666200 | 33333.34 | 1.2 | 40000.008
17 | 5.2 | 3 | 1185600 | 1205600 | 9090.91 | 2.2 | 20000.002
18 | 4.2 | 3 | 355200 | 395200 | 33333.34 | 1.2 | 40000.008
19 | 4.2 | 3 | 235200 | 285200 | 41666.67 | 1.2 | 50000.004
20 | 5 | 3 | 1000000 | 1100000 | 50000 | 2 | 100000
21 | 5.2 | 3 | 291200 | 301200 | 4545.46 | 3 | 13636.38
22 | 4 | 2 | 800000 | 850000 | 25000 | 2 | 50000
23 | 6.2 | 4 | 1413600 | 1463600 | 22727.28 | 2.2 | 50000.016
24 | 5 | 3 | 700000 | 750000 | 25000 | 2 | 50000
25 | 5.8 | 3 | 1647200 | 1667200 | 7142.86 | 3 | 21428.58
26 | 2 | 1 | 350000 | 380000 | 30000 | 1 | 30000
27 | 2 | 1 | 175000 | 195000 | 20000 | 1 | 20000
28 | 3.2 | 2 | 962600 | 1002600 | 33333.33 | 1.2 | 39999.996
29 | 2 | 1 | 426000 | 526000 | 100000 | 0 | 0
30 | 2 | 1 | 522000 | 592000 | 70000 | 1 | 70000
31 | 2 | 1 | 426000 | 496000 | 70000 | 1 | 70000
32 | 2.8 | 1 | 462000 | 482000 | 11111.11 | 1.8 | 19999.998
33 | 3 | 2 | 756000 | 796000 | 40000 | 1 | 40000
34 | 2 | 1 | 456000 | 484000 | 28000 | 1 | 28000
35 | 2 | 1 | 182000 | 192000 | 10000 | 1 | 10000
36 | 3 | 2 | 898000 | 918000 | 20000 | 1 | 20000
37 | 3 | 2 | 564000 | 594000 | 30000 | 1 | 30000
38 | 4.2 | 3 | 588000 | 608000 | 16666.67 | 1.2 | 20000.004
39 | 4.7 | 2 | 1560400 | 1590400 | 11111.11 | 2.7 | 29999.997
40 | 6 | 4 | 900000 | 930000 | 15000 | 2 | 30000
41 | 5.2 | 3 | 291200 | 301200 | 4545.46 | 3 | 13636.38
42 | 5 | 3 | 940000 | 970000 | 15000 | 2 | 30000
43 | 5.3 | 3 | 1123600 | 1143600 | 8695.65 | 3 | 26086.95
TOTALS |  |  | 35761000 |  |  | 75.3 | 1479038.355

## Crash Schedule
Project time | Period cost | Cumulative cost | Activities to crash
194 | 1457 | 1457 | 15 | Crash 15, 21, 41, 7, 25, 43, 9 by 3 weeks
193 | 1457 | 1457 | 15
191 | 3919.72 | 5336.4 | 15, 21
190 | 4545.46 | 9881.85 | 21
188 | 4545.46 | 14427.31 | 21, 41
187 | 4545.46 | 18972.76 | 41
185 | 5675.34 | 24648.1 | 7, 41
184 | 6428.57 | 31076.68 | 7
183 | 6428.57 | 37505.25 | 7
181 | 7000.01 | 44505.25 | 7, 25
180 | 7142.86 | 51648.11 | 25
178 | 7142.87 | 58790.98 | 25, 43
177 | 8695.65 | 67486.63 | 43
176 | 8695.65 | 76182.28 | 43
175 | 8908.7 | 85090.98 | 9, 43
174 | 9000 | 94090.98 | 9
173 | 9000 | 103091 | 9
Fixed Cost | 35000
Overhead Cost | 25000
Penalty Cost (>173 weeks ) | 40000
Total | 100000

## Cost After Crashing
Activity | Predecessor | Activity Time | Activity Cost
Start
Document Process
1. Define Project Scope |  | 5 | 1100000
2. Conduct Stackholder Analysis | 1 | 5.8333 | 1011200
3. Create Project Charter | 1,2 | 4.1667 | 588000
4. Identify Document Requirments | 3 | 4 | 560000
5. Obtain necessary permissons | 4 | 7 | 980000
6. Confirmation of Local Fire Department Partnership | 5 | 8.1667 | 1404800
7. Develop Safety Training Protocol | 6 | 4.8333 | 1846658
8. Review Documentation | 5,6,7 | 4.1667 | 924000
Training Preparation
9. Identify Learning Objectives | 8 | 3 | 1395000
10. Desing Training Materials Template | 9 | 4.1667 | 1041600
11. Develop Training Modules | 10 | 7 | 1344000
12. Design Lesson Plans | 9,11 | 5 | 960000
13. Create Interactive Activities | 12 | 6 | 1152000
14. Prepare Visual Aids | 11,13 | 6 | 864000
15. Gather Necessary Materials | 14 | 2.1667 | 803171
16. Secure Fire Extinguisher | 15 | 4.1667 | 626200
17. Co-ordinate with Fire Safety Experts | 16 | 5.1667 | 1185600
18. Schedule Training Sessions | 15,17 | 4.1667 | 355200
19. Arrange Transportation | 15,16,18 | 4.1667 | 235200
20. Assemble Training Kits | 18,19 | 5 | 1000000
21. Prepare Training Sign-Up Sheets | 17 | 2.1667 | 305046
22. Develop Pre-Assessment Tests | 21 | 4 | 800000
23. Train Instructors | 21,22 | 6.1667 | 1413600
24. Notify School Administrator | 20,23 | 5 | 700000
25. Finalize Training Agenda | 24 | 2.8333 | 1668376
Training Delivery
26. Conduct Pre-Assessment Tests | 25 | 2 | 350000
27. Set Up Training Ground | 26 | 2 | 175000
28. Deliver Training Modules | 25,27 | 3.1667 | 962600
29. Demostrate Fire Extinguisher Usage | 27 | 2 | 426000
30. Facilitate Interactive Activities | 27,28,29 | 2 | 522000
31. Provide Hands-On Training | 30 | 2 | 426000
32. Administer Post Assessment Tests | 30,31 | 2.8333 | 462000
33. Collect Training Evaluation Forms | 32 | 3 | 756000
34. Gather Feedback from Instructors | 33 | 2 | 456000
35. Gather Feedback From Students | 33,34 | 2 | 182000
Project Closure
36. Evaluate Effectiveness of Training | 34,35 | 3 | 898000
37. Review Feedback | 36 | 3 | 564000
38. Analyze Evaluation Data | 37 | 4.1667 | 588000
39. Conduct Post-Project Review Meeting | 38 | 4.6667 | 1560400
40. Share Results with Stackholders | 39 | 6 | 900000
41. Archive Project Documentation | 40 | 2.1667 | 305046
42. Farewell Party for Contributors | 41 | 5 | 940000
43. Close Project Accounts | 42 | 2.3333 | 1149314
Finish |  | 172.6667

## Cost Budgeting
| Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12 | Period 13 | Period 14 | Period 15 | Period 16 | Period 17 | Period 18 | Period 19 | Period 20 | Period 21 | Period 22 | Period 23 | Period 24 | Period 25 | Period 26 | Period 27 | Period 28 | Period 29 | Period 30 | Period 31 | Period 32 | Period 33 | Period 34 | Period 35 | Period 36 | Period 37 | Period 38 | Period 39 | Period 40 | Period 41 | Period 42 | Period 43 | Period 44 | Period 45 | Period 46 | Period 47 | Period 48 | Period 49 | Period 50 | Period 51 | Period 52 | Period 53 | Period 54 | Period 55 | Period 56 | Period 57 | Period 58 | Period 59 | Period 60 | Period 61 | Period 62 | Period 63 | Period 64 | Period 65 | Period 66 | Period 67 | Period 68 | Period 69 | Period 70 | Period 71 | Period 72 | Period 73 | Period 74 | Period 75 | Period 76 | Period 77 | Period 78 | Period 79 | Period 80 | Period 81 | Period 82 | Period 83 | Period 84 | Period 85 | Period 86 | Period 87 | Period 88 | Period 89 | Period 90 | Period 91 | Period 92 | Period 93 | Period 94 | Period 95 | Period 96 | Period 97 | Period 98 | Period 99 | Period 100 | Period 101 | Period 102 | Period 103 | Period 104 | Period 105 | Period 106 | Period 107 | Period 108 | Period 109 | Period 110 | Period 111 | Period 112 | Period 113 | Period 114 | Period 115 | Period 116 | Period 117 | Period 118 | Period 119 | Period 120 | Period 121 | Period 122 | Period 123 | Period 124 | Period 125 | Period 126 | Period 127 | Period 128 | Period 129 | Period 130 | Period 131 | Period 132 | Period 133 | Period 134 | Period 135 | Period 136 | Period 137 | Period 138 | Period 139 | Period 140 | Period 141 | Period 142 | Period 143 | Period 144 | Period 145 | Period 146 | Period 147 | Period 148 | Period 149 | Period 150 | Period 151 | Period 152 | Period 153 | Period 154 | Period 155 | Period 156 | Period 157 | Period 158 | Period 159 | Period 160
1 | Period 1: 220000; Period 2: 220000; Period 3: 220000; Period 4: 220000; Period 5: 220000
2 | Period 6: 174344.8; Period 7: 174344.8; Period 8: 174344.8; Period 9: 174344.8 | 174344.8
3 | [11 empty] | 140000 | 140000 | 140000 | 140000
4 | [15 empty] | 140000 | 140000 | 140000 | 140000
5 | [19 empty] | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000
6 | [26 empty] | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1
7 | [34 empty] | 384720.4 | 384720.4 | 384720.4 | 384720.4
8 | [39 empty] | 220000 | 220000 | 220000 | 220000
9 | [43 empty] | 465000 | 465000 | 465000
10 | [46 empty] | 248000 | 248000 | 248000 | 248000
11 | [50 empty] | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000
12 | [57 empty] | 192000 | 192000 | 192000 | 192000 | 192000
13 | [62 empty] | 192000 | 192000 | 192000 | 192000 | 192000 | 192000
14 | [68 empty] | 144000 | 144000 | 144000 | 144000 | 144000 | 144000
15 | [74 empty] | 365077.7 | 365077.7
16 | [77 empty] | 149095.3 | 149095.3 | 149095.3 | 149095.3
17 | [81 empty] | 228000 | 228000 | 228000 | 228000 | 228000
18 | [86 empty] | 84571.43 | 84571.43 | 84571.43 | 84571.43
19 | [90 empty] | 56000 | 56000 | 56000 | 56000
20 | [94 empty] | 200000 | 200000 | 200000 | 200000 | 200000
21 | [86 empty] | 138657.3 | 138657.3
22 | [88 empty] | 200000 | 200000 | 200000 | 200000
23 | [92 empty] | 228000 | 228000 | 228000 | 228000 | 228000 | 228000
24 | [99 empty] | 140000 | 140000 | 140000 | 140000 | 140000
25 | [104 empty] | 595848.6 | 595848.6
26 | [107 empty] | 175000 | 175000
27 | [109 empty] | 87500 | 87500
28 | [111 empty] | 300812.5 | 300812.5 | 300812.5
29 | [111 empty] | 213000 | 213000
30 | [114 empty] | 261000 | 261000
31 | [116 empty] | 213000 | 213000
32 | [118 empty] | 165000 | 165000
33 | [121 empty] | 252000 | 252000 | 252000
34 | [124 empty] | 228000 | 228000
35 | [126 empty] | 91000 | 91000
36 | [128 empty] | 299333.3 | 299333.3 | 299333.3
37 | [131 empty] | 188000 | 188000 | 188000
38 | [134 empty] | 140000 | 140000 | 140000 | 140000
39 | [138 empty] | 332000 | 332000 | 332000 | 332000
40 | [143 empty] | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
41 | [149 empty] | 138657.3 | 138657.3
42 | [151 empty] | 188000 | 188000 | 188000 | 188000 | 188000
43 | [156 empty] | 499701.8 | 499701.8
Total in Period | 220000 | 220000 | 220000 | 220000 | 220000 | 174344.8 | 174344.8 | 174344.8 | 174344.8 | 174344.8 | 0 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 140000 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 171317.1 | 384720.4 | 384720.4 | 384720.4 | 384720.4 | 0 | 220000 | 220000 | 220000 | 220000 | 465000 | 465000 | 465000 | 248000 | 248000 | 248000 | 248000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 192000 | 144000 | 144000 | 144000 | 144000 | 144000 | 144000 | 365077.7 | 365077.7 | 0 | 149095.3 | 149095.3 | 149095.3 | 149095.3 | 228000 | 228000 | 228000 | 228000 | 228000 | 223228.73 | 223228.73 | 284571.43 | 284571.43 | 256000 | 256000 | 284000 | 284000 | 428000 | 428000 | 428000 | 428000 | 200000 | 140000 | 140000 | 140000 | 140000 | 140000 | 595848.6 | 595848.6 | 0 | 175000 | 175000 | 87500 | 87500 | 513812.5 | 513812.5 | 300812.5 | 261000 | 261000 | 213000 | 213000 | 165000 | 165000 | 0 | 252000 | 252000 | 252000 | 228000 | 228000 | 91000 | 91000 | 299333.3 | 299333.3 | 299333.3 | 188000 | 188000 | 188000 | 140000 | 140000 | 140000 | 140000 | 332000 | 332000 | 332000 | 332000 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 138657.3 | 138657.3 | 188000 | 188000 | 188000 | 188000 | 188000 | 499701.8 | 499701.8 | 0 | 0
Cumulative from start | 220000 | 440000 | 660000 | 880000 | 1100000 | 1274344.8 | 1448689.6 | 1623034.4 | 1797379.2 | 1971724 | 1971724 | 2111724 | 2251724 | 2391724 | 2531724 | 2671724 | 2811724 | 2951724 | 3091724 | 3231724 | 3371724 | 3511724 | 3651724 | 3791724 | 3931724 | 4071724 | 4243041.1 | 4414358.2 | 4585675.3 | 4756992.4 | 4928309.5 | 5099626.6 | 5270943.7 | 5442260.8 | 5826981.2 | 6211701.6 | 6596422 | 6981142.4 | 6981142.4 | 7201142.4 | 7421142.4 | 7641142.4 | 7861142.4 | 8326142.4 | 8791142.4 | 9256142.4 | 9504142.4 | 9752142.4 | 10000142.4 | 10248142.4 | 10440142.4 | 10632142.4 | 10824142.4 | 11016142.4 | 11208142.4 | 11400142.4 | 11592142.4 | 11784142.4 | 11976142.4 | 12168142.4 | 12360142.4 | 12552142.4 | 12744142.4 | 12936142.4 | 13128142.4 | 13320142.4 | 13512142.4 | 13704142.4 | 13848142.4 | 13992142.4 | 14136142.4 | 14280142.4 | 14424142.4 | 14568142.4 | 14933220.1 | 15298297.8 | 15298297.8 | 15447393.1 | 15596488.4 | 15745583.7 | 15894679 | 16122679 | 16350679 | 16578679 | 16806679 | 17034679 | 17257907.73 | 17481136.46 | 17765707.89 | 18050279.32 | 18306279.32 | 18562279.32 | 18846279.32 | 19130279.32 | 19558279.32 | 19986279.32 | 20414279.32 | 20842279.32 | 21042279.32 | 21182279.32 | 21322279.32 | 21462279.32 | 21602279.32 | 21742279.32 | 22338127.92 | 22933976.52 | 22933976.52 | 23108976.52 | 23283976.52 | 23371476.52 | 23458976.52 | 23972789.02 | 24486601.52 | 24787414.02 | 25048414.02 | 25309414.02 | 25522414.02 | 25735414.02 | 25900414.02 | 26065414.02 | 26065414.02 | 26317414.02 | 26569414.02 | 26821414.02 | 27049414.02 | 27277414.02 | 27368414.02 | 27459414.02 | 27758747.32 | 28058080.62 | 28357413.92 | 28545413.92 | 28733413.92 | 28921413.92 | 29061413.92 | 29201413.92 | 29341413.92 | 29481413.92 | 29813413.92 | 30145413.92 | 30477413.92 | 30809413.92 | 30809413.92 | 30959413.92 | 31109413.92 | 31259413.92 | 31409413.92 | 31559413.92 | 31709413.92 | 31848071.22 | 31986728.52 | 32174728.52 | 32362728.52 | 32550728.52 | 32738728.52 | 32926728.52 | 33426430.32 | 33926132.12 | 33926132.12 | 33926132.12
| Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12 | Period 13 | Period 14 | Period 15 | Period 16 | Period 17 | Period 18 | Period 19 | Period 20 | Period 21 | Period 22 | Period 23 | Period 24 | Period 25 | Period 26 | Period 27 | Period 28 | Period 29 | Period 30 | Period 31 | Period 32 | Period 33 | Period 34 | Period 35 | Period 36 | Period 37 | Period 38 | Period 39 | Period 40 | Period 41 | Period 42 | Period 43 | Period 44 | Period 45 | Period 46 | Period 47 | Period 48 | Period 49 | Period 50 | Period 51 | Period 52 | Period 53 | Period 54 | Period 55 | Period 56 | Period 57 | Period 58 | Period 59 | Period 60 | Period 61 | Period 62 | Period 63 | Period 64 | Period 65 | Period 66 | Period 67 | Period 68 | Period 69 | Period 70 | Period 71 | Period 72 | Period 73 | Period 74 | Period 75 | Period 76 | Period 77 | Period 78 | Period 79 | Period 80 | Period 81 | Period 82 | Period 83 | Period 84 | Period 85 | Period 86 | Period 87 | Period 88 | Period 89 | Period 90 | Period 91 | Period 92 | Period 93 | Period 94 | Period 95 | Period 96 | Period 97 | Period 98 | Period 99 | Period 100 | Period 101 | Period 102 | Period 103 | Period 104 | Period 105 | Period 106 | Period 107 | Period 108 | Period 109 | Period 110 | Period 111 | Period 112 | Period 113 | Period 114 | Period 115 | Period 116 | Period 117 | Period 118 | Period 119 | Period 120 | Period 121 | Period 122 | Period 123 | Period 124 | Period 125 | Period 126 | Period 127 | Period 128 | Period 129 | Period 130 | Period 131 | Period 132 | Period 133 | Period 134 | Period 135 | Period 136 | Period 137 | Period 138 | Period 139 | Period 140 | Period 141 | Period 142 | Period 143 | Period 144 | Period 145 | Period 146 | Period 147 | Period 148 | Period 149 | Period 150 | Period 151 | Period 152 | Period 153 | Period 154 | Period 155 | Period 156 | Period 157 | Period 158 | Period 159 | Period 160
Cumulative from start | 220000 | 440000 | 660000 | 880000 | 1100000 | 1274344.8 | 1448689.6 | 1623034.4 | 1797379.2 | 1971724 | 1971724 | 2111724 | 2251724 | 2391724 | 2531724 | 2671724 | 2811724 | 2951724 | 3091724 | 3231724 | 3371724 | 3511724 | 3651724 | 3791724 | 3931724 | 4071724 | 4243041.1 | 4414358.2 | 4585675.3 | 4756992.4 | 4928309.5 | 5099626.6 | 5270943.7 | 5442260.8 | 5826981.2 | 6211701.6 | 6596422 | 6981142.4 | 6981142.4 | 7201142.4 | 7421142.4 | 7641142.4 | 7861142.4 | 8326142.4 | 8791142.4 | 9256142.4 | 9504142.4 | 9752142.4 | 10000142.4 | 10248142.4 | 10440142.4 | 10632142.4 | 10824142.4 | 11016142.4 | 11208142.4 | 11400142.4 | 11592142.4 | 11784142.4 | 11976142.4 | 12168142.4 | 12360142.4 | 12552142.4 | 12744142.4 | 12936142.4 | 13128142.4 | 13320142.4 | 13512142.4 | 13704142.4 | 13848142.4 | 13992142.4 | 14136142.4 | 14280142.4 | 14424142.4 | 14568142.4 | 14933220.1 | 15298297.8 | 15298297.8 | 15447393.1 | 15596488.4 | 15745583.7 | 15894679 | 16122679 | 16350679 | 16578679 | 16806679 | 17034679 | 17257907.73 | 17481136.46 | 17765707.89 | 18050279.32 | 18306279.32 | 18562279.32 | 18846279.32 | 19130279.32 | 19558279.32 | 19986279.32 | 20414279.32 | 20842279.32 | 21042279.32 | 21182279.32 | 21322279.32 | 21462279.32 | 21602279.32 | 21742279.32 | 22338127.92 | 22933976.52 | 22933976.52 | 23108976.52 | 23283976.52 | 23371476.52 | 23458976.52 | 23972789.02 | 24486601.52 | 24787414.02 | 25048414.02 | 25309414.02 | 25522414.02 | 25735414.02 | 25900414.02 | 26065414.02 | 26065414.02 | 26317414.02 | 26569414.02 | 26821414.02 | 27049414.02 | 27277414.02 | 27368414.02 | 27459414.02 | 27758747.32 | 28058080.62 | 28357413.92 | 28545413.92 | 28733413.92 | 28921413.92 | 29061413.92 | 29201413.92 | 29341413.92 | 29481413.92 | 29813413.92 | 30145413.92 | 30477413.92 | 30809413.92 | 30809413.92 | 30959413.92 | 31109413.92 | 31259413.92 | 31409413.92 | 31559413.92 | 31709413.92 | 31848071.22 | 31986728.52 | 32174728.52 | 32362728.52 | 32550728.52 | 32738728.52 | 32926728.52 | 33426430.32 | 33926132.12 | 33926132.12 | 33926132.12